Project Proposal: Autumn Gala 2026

Prepared by: Christine Schott

Date: 1 May 2026

Executive Summary

This proposal outlines the plan for the autumn fundraising gala, targeting a net raise of £40,000 for the community arts centre restoration fund.

Objectives

1. Secure a minimum of 8 sponsors at Supporting level or above

2. Sell 180 of 200 available seats

3. Run a silent auction with a minimum of 20 lots

Budget

Venue: £4,800

Catering: £3,200

Marketing: £1,200

AV Equipment: £800

Miscellaneous: £320

Total costs: £10,320

Target income: £50,320

Net raise: £40,000

Timeline

2 June       Venue confirmed

15 June      Sponsor packs distributed

1 July       Ticket sales open

1 September  Event date